## Guide
© 2025 Zohar Strinka - Meta-problem.com
Recommended Workflow
Step 1: Create a list of tasks with at least one proposed method to address it
Step 2: Estimate the value to the business of completing the task with the proposed method. Include a lower and upper bound on how valuable the solution will be considering how useful the solution may be or how well adopted.
Step 3: Estimate the development cost and future ongoing maintenance costs. Include a lower and upper bound on how much development cost it will take to develop the solution with the proposed method.
Step 4: If there is a range on the value estimate or the development cost, identify opportunities to reduce that uncertainty by research spikes before committing to a specific solution method.
Step 5: Choose whether to pursue research to reduce the unknown or if there is enough known to priorize a given task being completed via a method.
The sample use case is related to building a data warehouse

## Backlog
© 2025 Zohar Strinka - Meta-problem.com
Task | Method | Value - Lower Bound (1 is lowest, 5 is highest) | Value - Upper Bound (1 is lowest, 5 is highest) | Development Cost - Lower Bound (1 is lowest, 5 is highest) | Development Cost - Upper Bound (1 is lowest, 5 is highest) | Operational costs (1 is lowest, 5 is highest) | Research cost to reduce value range by 1 | Research cost to reduce effort range by 1 | Uncertainty Score | Cost to reduce uncertainty | Scaled Priority | Comments
Ingest Sales Data | Fivetran | 2 | 2 | 1 | 1 | 3 |  |  | 0 |  | 1.4 | Easy to set up, high confidence in the value and effort, but higher operational costs when done.
Ingest Sales Data | Matillion | 2 | 2 | 1 | 2 | 2 |  | 3 | 1 | 3 | 0.93333 | Alternative method to the row above. The value is the same since the output will be the same, but it may take additional development effort in exchange for lower operational costs.
Clean Product data | Excel | 1 | 2 | 1 | 1 | 3 | 2 |  | 1 | 2 | 0.9 | The value is relatively low since an excel solution is typically pretty limited for data modeling. However, it is easy to build. Operational costs are high if we actually want to maintain a spreadsheet solution.
Clean Product data | Data Warehouse | 2 | 4 | 3 | 5 | 1 | 2 | 2 | 4 | 2 | 0.55 | The value can be quite high to doing the work of creating a full data model of your products. However, the effort is also often high (and uncertain) to build these features. Operational costs are typically low once development is complete
Create Sales by Category visual | Excel | 1 | 1 | 1 | 1 | 1 |  |  | 0 |  | 0.8 | Building a data visual in excel is easy, but typically not very useful.
Create Sales by Category visual | Power BI | 1 | 3 | 1 | 1 | 1 |  |  | 2 |  | 1.8 | The value of building a sales by category in an analytics tool typically comes with greater flexibility that increases the value of the solution. The work is usually quite low, assuming you already have a working connection to the data.